## project WBS monitor
project: |  |  |  | remark | WBS id is reference to chapter in functional design (FD)
calculator: |  |  |  | remark | for FD: chapter are not chronological
date: |  |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration, hr (plan) | duration, hr (do) | evaluation (check) | action (act)
1 |  | documentatie | M | J, L |  | 2 | 1
2 |  | MIDI player class maken | M | J |  | 5 | 1 | ready
3 |  | MIDI reader class maken | M | L |  | 6 | 5 | ready
4 |  | Timeline Interface | M | J, L |  | 20 | 15
5 |  | RGB Spot aansluiten | M | L |  | 4 | 3 | ready
6 |  | Spiegellamp | M | J, L |  | 4 | 2
7 |  | Lazer aansluiten | M | J, L |  | 10 | 2 | ready
8 |  | Visuele Events | M | L |  | 5 | 2 | ready
9 |  | Classes aanmaken voor iedere spot | M | J |  | 9 | 10
10 |  | Zoom | S | J, L |  | 6
11 |  | Custom window border | S | J |  | 3
12
13
14
15
16
17
18
|  | total |  |  |  | 74 | 41

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma